## To-do list
2025 | STOCK TO-TO-LIST
Task | Priority | Status | Start date | Due date | % Complete | Column1 | Done/Overdue? | Notes
run "db_manager" -"reset_and_populate_actions_sectors_and_stocks_tables" | Normal | Complete | 2024-01-28 | 2024-01-28 | 100% |  | 1
un "reader_tests"-"test_get_stock_pe_ratio" with sector="Utilties" stock= "NEE" | Normal | Complete | 2024-01-28 | 2024-01-28 | 100% |  | 1
change buy/sell score from specified value to percentage of total score | Normal | Complete | 2024-01-31 | 2024-01-31 | 100% |  | 1
run "screener_tests"-"test_update_sector_median_positive_pe_ratio" with sector=""Information Technology" | Normal | Complete | 2024-02-02 | 2024-02-02 | 100% |  | 1
run "screener_tests"-"test_insert_stat_history" with portfolio stock="NEE" | Normal | Complete | 2024-02-01 | 2024-02-01 | 100% |  | 1
add gramNumber weight to metric_weights and total_score calc. | Normal | Complete | 2024-02-13 | 2024-02-13 | 100% |  | 1
remove eval action from all stocks, use top 5 sector scores to evaluate individual stocks, set action to eval. | High | Complete | 2024-02-13 | 2024-02-13 | 100% |  | 1
sort sector screen results, only use top 5 scores | Normal | Complete | 2024-02-04 | 2024-02-14 | 100% |  | 1
run "screener_tests"-"test_screen_sector stocks" with sector=""Information Technology" | Normal | Complete | 2024-01-28 | 2024-02-14 | 100% |  | 1
Created screen_portfolio_stocks.py & screen_portfolio_stocks.bat. Modified Task Schedular -> Stock Screener to run screen_portfolio_stocks.bat. | High | Complete | 2024-02-15 | 2024-02-15 | 100% |  | 1
Alter stocks table (remove unused "monitor" fields) | High | Complete | 2024-04-11 | 2024-04-11 | 100% |  | 1
Alter recent_screened_stocks table (add metrics) | High | Complete | 2024-04-11 | 2024-04-11 | 100% |  | 1
Create portfolio_metric_history table | High | Complete | 2024-04-07 | 2024-04-11 | 100% |  | 1
Schedule portfolio stocks screen for one month intervals. | High | Complete | 2024-04-13 | 2024-04-13 | 100% |  | 1
display recient_screened_stocks (top_five + portfolio) on screener page | High | Complete | 2024-03-26 | 2024-04-13 | 100% |  | 1
validate metric calcs. & weights & consider others for use | High | Complete | 2024-05-09 | 2024-05-30 | 100% |  | 1
consider other metrics peRatio(trailing/forware)… | High | Complete | 2024-06-01 | 2024-06-06 | 100% |  | 1
add high, mid, low ranges to metric_weights table | High | Complete | 2024-07-08 | 2024-07-31 | 100% |  | 1
refactor portfolioi_metric_weights - Server apis Client secreener & admin. | High | Complete | 2024-06-11 | 2024-07-04 | 100% |  | 1
Create Stock Evaluation Excel Table | High | Complete | 2024-07-27 | 2024-08-30 | 100% |  | 1
Use Piotorski F-score for initial screeneing… | High | Complete | 2024-07-29 | 2024-08-30 | 100% |  | 1
Use following value indicators: peRatio, ROE, ROA, EPS, dividend yield, esg-scores, price-to-book, debt_to_equity, free_cashflow_per_share, peg_ratio, qick_ratio, debt_to_asset_ratio | High | Complete | 2024-07-30 | 2024-09-16 | 100% |  | 1
Refactor metricss - Server apis Client analyzer | High | Complete | 2024-09-13 | 2024-10-15 | 100% |  | 1
Fix Porffolio Metric History Chart y-axis map | High | Complete | 2024-10-03 | 2024-10-05 | 100% |  | 1
Depoly to Laptop | High | Complete | 2024-10-10 | 2024-10-11 | 100% |  | 1
Update MySQL Workbench | High | Complete | 2024-10-12 | 2024-10-12 | 100% |  | 1
Research Graham Number Formula | High | Complete | 2024-10-17 | 2024-10-30 | 100% |  | 1
Fix fscore calc. | High | Complete | 2024-11-25 | 2024-11-30 | 100% |  | 1
Refactor logging | Normal | Complete | 2025-01-10 | 2025-01-31 | 100% |  | 1
Refactor screened and portfolio history tables & chart api for empty db tables | Normal | Complete | 2025-01-10 | 2025-01-31 | 100% |  | 1
Create "Eval" Daily Returns Chart | Normal | Complete | 2025-01-26 | 2025-01-30 | 100% |  | 1
Create Portfolio_metric_history table Backup DB Manager Item | Normal | Complete | 2025-01-26 | 2025-02-08 | 100% |  | 1
Remove is_date_ok from inserting portfolio_metric_history & portfolio_stat_history | Normal | Complete | 2025-02-25 | 2025-02-25 | 100% |  | 1
Fix Stock Analyzer -> Portfolio Metric History | Normal | Complete | 2025-06-20 | 2025-06-30 | 100% |  | 1
Add "Avg. Cost" cost to "Stock Chart" | Normal | Complete | 2025-09-16 | 2025-09-28 | 100% |  | 1
Add Sold to Acquisitions | Normal | Complete | 2025-09-28 | 2025-10-14 | 100% |  | 1
Fix Stock Analyzer -> Retunrs Chart -> Evaulate | Normal | Complete | 2025-10-03 | 2025-10-10 | 100% |  | 1
Fix Graham Number Calc.. | Normal | In Progress | 2025-10-04 | 2025-10-15 | 0% |  | 0
Fix "Ticker Stat Charts" | High | Complete | 2025-10-08 | 2025-10-20 | 100% |  | 1
Hide/Show Sector 'Sectors" table. | Normal | Not Started | 2025-10-12 |  |  |  | -1
Add back mean P/E Ratio | Normal | Not Started | 2025-10-12 |  |  |  | -1
Add "Split" to aquasiions | Normal | Complete | 2025-10-16 | 2025-10-17 | 100% |  | 1
-1
-1
NEW ITEM | [6 empty] | -1